## Sheet1
Amenities Committee - Monitoring Report
Date | Item | Minute | Lead | Timescales / Progress
Green box means completed
2021-11-15 | Arboricultural Assessments & Tree Risk Strategy | A/21/73 | Andrew Chapman-New | Areas have been 'zoned' Ranger to assess high risk areas with Bengers, in conjunction with Tree Risk Strategy, Ranger working on updated document
2022-07-18 | Community Garden | A/22/51 | Andrew Chapman-New | Grant funding achieved, CIC has arranged for Co-Create to support set up. Ranger has updated volunteers and local schools and invited engagement through Design competition. Water Trough installed subject to minor changes.
2022-07-18 | Happy to Chat Bench | A/22/50 | Andrew Chapman-New | Update report to consider alternative benches and locations for installation - to be brought to Committee Spring 2024
2022-10-10 | Biodiversity Study | A/22/66 | Andrew Chapman-New | Ranger report to Committee January 2024
2022-12-05 | Memorial Benches | A/22/73 | Andrew Chapman-New | Ranger to review scheme for commemorative Memorial Benches in the Country Park Spring 2024
2023-05-22 | St Martins - Path Remediation | A/23/33 & A/23/55 | Alex Robinson | Awaiting dates and works schedule from Grounds Maintenance Contractor likely to be after 15/4/24
2023-07-17 | Great Meadow - Fencing | A/23/46 A/23/57 | Andrew Chapman-New | Ranger has cleared one section creating new pathway and intends to make second gap and pathway.
2023-10-09 | Nature Reserve | A/23/58 | Andrew Chapman -New & Cllr Les Bayliss | Delegated to Ranger in consultation with Cllr Les Bayliss to seek options for the area within Great Meadow. To bring updated report with associated costs to future meeting.
2023-10-09 | Sustainable Urban Drainage System SUDS | A/23/60 | Andrew Chapman-New | Ranger to confirm existing contractual arrangements for grass cutting around the SUDS and provide clarification on who will clear the leats and ditches in updated report to future meeting. March 2024
2024-01-29 | Provision of Tramper Mobility Scooter |  | Andrew Chapman -New & Alex Robinson | Initial discussion with representatives from LiveWest and Countryside Mobility with Cllr Ray Bloxham, AC-N and AR. Report to Committee to consider support and establish working group to investigate further.
2024-01-29 | Play Area - Gates |  | Sophie Anderson & Alex Robinson | Report to Committee to summarise remediation to self-closing gates